## Delivery Plan
ID | Phase | Activity | Deliverable | Owner | Dependency | Indicative duration | Status
P01 | Discover | Confirm scope and governance | Approved project brief | Sponsor / Project lead | Sponsor availability | 1 week | Not started
P02 | Discover | Interview process owners and users | Interview notes; pain-point log | Business analyst | P01 | 1 week | Not started
P03 | Discover | Map current-state workflows | Validated process maps | Business analyst | P02 | 1 week | Not started
P04 | Define | Prioritise business requirements | Approved requirements register | Process owners | P03 | 1 week | Not started
P05 | Define | Review future-state processes and controls | Process design sign-off | Process owners | P04 | 1 week | Not started
P06 | Prepare | Profile, cleanse and map master data | Data checklist and mapping | Data lead | P05 | 2 weeks | Not started
P07 | Prepare | Configure solution and integrations | Configuration evidence | Vendor / IT | P05 | Estimate required | Not started
P08 | Prepare | Develop role-based training | Training pack | Change lead | P05, P07 | 1 week | Not started
P09 | Validate | Prepare UAT scenarios and test data | Approved UAT pack | BA / Process owners | P04, P07 | 1 week | Not started
P10 | Validate | Execute UAT and triage defects | Test evidence and defect log | Business testers | P09 | 2 weeks | Not started
P11 | Deploy | Rehearse migration and cutover | Cutover checklist | IT / Data lead | P06, P10 | 1 week | Not started
P12 | Deploy | Conduct go/no-go review | Signed readiness decision | Sponsor | P10, P11 | 1 day | Not started
P13 | Deploy | Go-live and communications | Go-live record | Project lead | P12 | As scheduled | Not started
P14 | Stabilise | Monitor incidents and KPIs | Hypercare log | Support / Process owners | P13 | 2–4 weeks | Not started
P15 | Stabilise | Handover to BAU and close | BAU acceptance; lessons learned | Project lead | P14 | 1 week | Not started