## Stakeholders
Stakeholder | Role | Interest | Influence | Engagement | Key input | Owner | Status
Executive sponsor | Sponsor | High | High | Monthly steering; decision papers | Scope, funding, go/no-go | Project lead | To confirm
Sales leadership | Process owner | High | High | Discovery and design workshops | Order capture, customer impact | Project lead | To confirm
Inventory / warehouse | Process owner | High | High | Walkthroughs and prototype reviews | Stock, receiving, fulfilment | Project lead | To confirm
Finance | Process owner | High | High | Control and reconciliation workshops | Invoice matching, reporting | Project lead | To confirm
IT / vendor | Technical delivery | High | High | Design sessions and checkpoints | Configuration, integrations, migration | Project lead | To confirm
Frontline users | End users | High | Medium | Interviews, demos and training | Usability and exception handling | Change lead | To confirm
Super users | Change champions | High | Medium | Working group and UAT | Scenario validation and peer support | Process owners | To confirm