## UAT Cases
Test ID | Requirement | Process | Scenario | Preconditions / data | Test steps | Expected result | Actual result | Status | Defect ID | Tester
UAT-001 | BR-01 | Order-to-cash | Create valid customer order | Active customer; valid item; stock available | Enter customer and item; submit order | Order saves with unique reference |  | Not run
UAT-002 | BR-01 | Order-to-cash | Reject missing mandatory field | Customer or item omitted | Create order; leave required field blank; submit | Submission blocked; missing field identified |  | Not run
UAT-003 | BR-02 | Inventory | Display available stock | Known on-hand and reserved quantities | Search item; compare displayed availability | Availability matches approved stock rules |  | Not run
UAT-004 | BR-03 | Procure-to-pay | Record partial goods receipt | PO for 10; receive 7 | Open PO; record 7 received; save | 7 received; 3 outstanding; audit trail retained |  | Not run
UAT-005 | BR-04 | Procure-to-pay | Route purchase request for approval | Request above approval threshold | Create and submit request; inspect queue | Routes to authorised approver; decision recorded |  | Not run
UAT-006 | BR-05 | Finance | Flag invoice quantity mismatch | Invoice and receipt quantities differ | Enter invoice; run matching; review | Mismatch flagged and held for review |  | Not run
UAT-007 | BR-06 | Reporting | Filter inventory exceptions | Records across statuses and dates | Open report; apply date/status filters | Results match filters and source records |  | Not run
UAT-008 | BR-07 | Master data | Prevent incomplete product record | Mandatory category or unit omitted | Create product; omit field; save | System blocks or flags record as designed |  | Not run
UAT-009 | BR-08 | Security | Restrict finance access | Sales-only test account | Sign in; attempt finance-only action | Access denied; event logged where required |  | Not run
UAT-010 | BR-01 / BR-02 | End-to-end | Complete order through dispatch | Valid customer and stock | Create order; reserve; fulfil; dispatch | Order and stock status update consistently |  | Not run